## Time_table
Working Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Start of the week | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09
Sensing and input working package | 2021-11-22: Documentation on the given guides and projects. Chose main languages and technologies Create/adapt project plan Members tasks asignation; 2021-11-29: Camera handling, preprocessing, noise cancelling, ROIs definition; 2022-01-17: Define other necessary sensors, define use-case, integration (IMU, distance), preprocessing, noise cancelling.; 2022-05-09: BFMC
Define use-case and test given servers information (localisation on map, cars interaction, gps interaction)
[18 empty] | Induce noise on all sensors and systems |  |  |  | Other functionalities and optimizations
Perception and scene understanding working package | 2021-11-29: Lane detection; 2021-12-27: Intersection detection; 2022-01-24: Traffic sign detection; 2022-02-21: Traffic light detection
[12 empty] | Position fusion | [5 empty] | Traffic lights detection & classification
[14 empty] | Define objects properties file |  |  |  | Object detection & classification
Environmental server interaction
Other functionalities and optimizations
Behaviour and motion plan working package | 2021-11-29: Define project architecture and communication between packages; 2022-01-24: Define path planning and validation; 2022-02-21: Define robustness and safety measures
Define decision making --> priorities of actions and state flow
[18 empty] | Induce noise on systems to valdiate robustness (loss of image, burned image, road search, undefined objects and states) |  |  |  | Other functionalities and optimizations
Vehicle control working packages | 2021-11-29: Lane following and speed control; 2022-01-24: Intersection navigation; 2022-02-21: Simpla action taking maneuvers (parking, stop for traffic sign, stop for traffic light, stop for pedestrian); 2022-03-21: Complex action taking maneuvers (swith lane for static and mobile car, road search)
Other functionalities and optimizations
Final result & Demo | 2021-11-22: Team can control the phisical car remotely and the virtual car on the simulator.; 2021-11-29: Robot can keep a lane, can make a curve; 2022-01-24: Robot can navigate in intersection; 2022-02-21: Robot can go on a pre-determined path, stop at stop sign, park at parking sign, slow at crosswalk; 2022-03-21: While detecting and calculating it's position, the robot can dynamicaly go to specified checkpoint, react to traffic lights, interact with other cars and send environemt data)
|  | Team defines and creates it's own phisical testing environment |  |  |  | Team defines a way of parallel developing and testing
Team installs the virtual testing environment
Other functionalities and optimizations
Deadlines | 2021-12-13: 2021-12-19; 2022-01-17: 2022-01-23; 2022-02-14: 2022-02-20; 2022-03-14: 2022-03-20; 2022-04-11: 2022-04-17; 2022-05-09: 2022-05-15
Checkpoint | 2021-12-13: 1st report; 2021-12-20: Christmas brake; 2022-01-17: 2nd report; 2022-02-14: 3rd report; 2022-03-14: Mid-term quality gate; 2022-04-11: 4th report; 2022-05-09: Finals